COMMONWEALTH OF VIRGINIA

DEPARTMENT OF TRANSPORTATION

COMPUTATION OF EXTENSION OF TIME AND OF LIQUIDATED DAMAGES OR BONUS

| Date: |  |
| --- | --- |

| Project No.: |  | Contract ID No.: |  |
| --- | --- | --- | --- |
| County: |  | Route: |  |

| Project/Schedule: |  |
| --- | --- |

| Date Bids Received: |  | Date Contractor Notified to Start Work On: |  |
| --- | --- | --- | --- |
| Date Work Started: |  | Contract Time in Days: |  |

| Contract Time Limit Date: |  |
| --- | --- |

| Cost of Work to Date | $ |
| --- | --- |
| Adjustment For Non-Compliance |  |

| Net Cost of Work | $ |
| --- | --- |

| Dollar Value of Original Contract | $ |
| --- | --- |
| Total Face Value of Work Orders | $ |

| Adjusted Contract Value | $ |
| --- | --- |
| Dollar Value of Extra Work | $ |

| The dollar value of the original contract | $ | divided by the Contract Time in Days |  |
| --- | --- | --- | --- |

| equal Daily Dollar Value of | $ |
| --- | --- |

| The Dollar Value of Extra Work | $ | divided by the Daily Dollar Value | $ |
| --- | --- | --- | --- |

| equals |  | days time extension for extra work. |
| --- | --- | --- |

| Contract Time Limit Date |  | , plus |  | days for extra work, |  | days specified on |
| --- | --- | --- | --- | --- | --- | --- |

| Work Orders, |  | days Shutdown and |  | days (see remarks) equals |  | Extended Time Limit. |
| --- | --- | --- | --- | --- | --- | --- |

| Work was completed |  |
| --- | --- |

| Between |  | extended time limit date and |  | date work was completed, |
| --- | --- | --- | --- | --- |

| there are |  | calendar days at |  | per day equals |  | (liquidated damages) |
| --- | --- | --- | --- | --- | --- | --- |

(bonus).

Remarks: