## Sheet1
2010 SCHEDULE
FOR SUBMISSION OF INFORMATION FOR PROJECT APPROVAL
BY THE COMMONWEALTH TRANSPORTATION BOARD
CTB MEETING DATE | CTB PACKAGE TO | CTB PACKAGE TO | PROJECT INFORMATION | TRANSCRIPTS
(TYPICALLY THE 3RD THURSDAY) | Malcolm T. Kerley | Mohammad Mirshahi
| CHIEF ENGINEER FOR APPROVAL AND FORWARDING TO CTB | STATE L&D ENGINEER FOR REVIEW & RECOMMENDATION TO CHIEF ENGINEER | DA OR DESIGNEE SUBMITS TO ASSISTANT STATE L&D ENGINEER | PM SUBMITS PACKAGE TO DA OR DESIGNEE
| (1) | (2) | (3) | (4)
2010-01-20 | 2010-01-03 | 2009-12-24 | 2009-12-17 | 2009-12-10
2010-02-17 | 2010-01-31 | 2010-01-21 | 2010-01-14 | 2010-01-07
2010-03-17 | 2010-02-28 | 2010-02-18 | 2010-02-11 | 2010-02-04
2010-04-15 | 2010-03-29 | 2010-03-19 | 2010-03-12 | 2010-03-05
2010-05-20 | 2010-05-03 | 2010-04-22 | 2010-04-15 | 2010-04-08
2010-06-17 | 2010-05-31 | 2010-05-21 | 2010-05-14 | 2010-05-07
2010-07-15 | 2010-06-28 | 2010-06-18 | 2010-06-11 | 2010-06-04
No Board Meeting | 2010-07-31 | 2010-07-21 | 2010-07-10 | 2010-07-02
2010-09-16 | 2010-08-30 | 2010-08-20 | 2010-08-13 | 2010-08-06
2010-10-21 | 2010-10-04 | 2010-09-24 | 2010-09-17 | 2010-09-10
2010-11-18 | 2010-11-01 | 2010-10-22 | 2010-10-15 | 2010-10-08
2010-12-15 | 2010-11-28 | 2010-11-18 | 2010-11-11 | 2010-11-04
| (1)- 17 DAYS BEFORE SCHEDULED CTB MEETING, STATE L&D ENGINEER SUBMITS RECOMMENDATION TO CHIEF ENGINEER | (2)-Ten (10) DAYS BEFORE SUBMISSION TO CHIEF ENGINEER, RECOMMENDATION DUE FROM ASST. L&D ENGR. OR S&B ENGR. | (3) ASSISTANT STATE L&D ENGINEER COORDINATES REVIEW & COMMENTS WITH FHWA & ATTORNEY GENERAL & SUBMITS RECOMMENDATION TO STATE L&D ENGINEER | (4) DA OR DESIGNEE DISTRIBUTES TO LOCAL CTB REP., (LOCAL GOVERNMENT RESOLUTION, IF PREFERRED BY DISTRICT, DUE BY THIS DATE)
Formulas:
CTB PACKAGE TO = SUM([CTB MEETING DATE]-17)
CTB PACKAGE TO = SUM([CTB PACKAGE TO]-10)
PROJECT INFORMATION = SUM([CTB PACKAGE TO]-7)
TRANSCRIPTS = SUM([PROJECT INFORMATION]-7)