## Sheet1
SCHEDULE FOR SUBMISSION OF INFORMATION
FOR PROJECT APPROVAL TO THE CHIEF ENGINEER OR APPROVAL BY
COMMONWEALTH TRANSPORTATION BOARD FOR 2008
CTB MEETING DATE | CTB PACKAGE TO | CTB PACKAGE TO | PROJECT INFORMATION | TRANSCRIPTS SUBMITTED
(3RD , THURSDAY) | Malcolm T. Kerley | Mohammad Mirshahi | (RECOMMENDATION)
or signature by | CHIEF ENGINEER for | State L & D Engineer | TO PUBLIC INVOLVEMENT | TO PUBLIC INVOLVEMENT
Chief Engineer for |  | FOR REVIEW | SECTION | SECTION FOR DISTRIBUTION
Project Development | (1) | (2) | (3) | (4)
Des approval or CTB frwd
2008-01-17 | 2007-12-31 | 2007-12-21 | 2007-12-14 | 2007-12-07
2008-02-21 | 2008-02-04 | 2008-01-25 | 2008-01-18 | 2008-01-11
2008-03-20 | 2008-03-03 | 2008-02-22 | 2008-02-15 | 2008-02-08
2008-04-17 | 2008-03-31 | 2008-03-21 | 2008-03-14 | 2008-03-07
2008-05-15 | 2008-04-28 | 2008-04-18 | 2008-04-11 | 2008-04-04
2008-06-19 | 2008-06-02 | 2008-05-23 | 2008-05-16 | 2008-05-09
2008-07-17 | 2008-07-01 | 2008-06-21 | 2008-06-14 | 2008-06-07
No Board Meeting | 2008-07-31 | 2008-07-21 | 2008-07-14 | 2008-07-07
2008-09-18 | 2008-09-01 | 2008-08-22 | 2008-08-15 | 2008-08-08
2008-10-16 | 2008-09-29 | 2008-09-19 | 2008-09-12 | 2008-09-05
2008-11-05 | 2008-10-19 | 2008-10-09 | 2008-10-02 | 2008-09-25
2008-12-18 | 2008-12-01 | 2008-11-21 | 2008-11-14 | 2008-11-07
| (1)- 17 DAYS BEFORE | (2)-Ten (10) DAYS | (3) RECOMMENDATION DUE | (4) TRANSCRIPTS, RESIDENT ENGR.
| SCHEDULED CTB | BEFORE SUBMISSION | FROM ASST. L&D ENGR. | DIST. CONST. ENGR, CITY,
| MEETING | TO CHIEF ENGINEER | S&B ENGR., SECONARY RD, | TOWN, COUNTIES RESOLUTIONS
|  |  | URBAN ENGR, ENVR. ENGR. | IS DUE ON THIS DATE
Formulas:
CTB PACKAGE TO = SUM([CTB MEETING DATE]-17)
CTB PACKAGE TO = SUM([CTB PACKAGE TO]-10)
PROJECT INFORMATION = SUM([CTB PACKAGE TO]-7)
TRANSCRIPTS SUBMITTED = SUM([PROJECT INFORMATION]-7)